| Project Management | Date |
| --- | --- |

|  | Urgent |  | For Review |  | Please Comment |  | Please Reply |  | Please Recycle |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| From: | Scelo Kevin Nyandeni |
| --- | --- |
| Phone: | 230189695 |
| Fax: | 230189695@mycput.ac.za |

Comments:

[Type comments]

- Refined WBS with Defined Activities & Milestones

1.0 Initiation

1.1 Define project goals and scope

1.2 Identify stakeholders

1.3 Appoint project team

  - Project Charter Completed

2.0 Planning

2.1 Conduct stakeholder analysis

2.2 Develop requirements traceability matrix

2.3 Develop project schedule and budget

2.4 Create risk management plan

2.5 Planning Phase Approved

3.0 Design

3.1 Create UI/UX wireframes

3.2 Define technical architecture

3.3 Develop data models

3.4 Design Sign-Off Received

4.0 Development

4.1 Build front-end interface

4.2 Develop back-end functionality

4.3 Integrate shuttle tracking system

4.4 Connect database and API

4.5 System Prototype Ready

5.0 Testing

5.1 Perform unit testing

5.2 Conduct integration testing

5.3 Execute user acceptance testing (UAT)

5.4 Final Approval from Stakeholders

6.0 Deployment

6.1 Deploy system on server

6.2 Train staff and students

6.3 Monitor system performance

6.4 Project Completion & Handover

- Logical Network of Sequenced Activities with Dependencies

| ID | Activity | Depends On | Type of dependency |
| --- | --- | --- | --- |
| A | Define project goals and scope. | _ | _ |
| B | Identify stakeholders | A | Finish-to-Start |
| C | Appoint project team | A | Finish-to-Start |
| D | Conduct stakeholder analysis | B, C | Finish-to-Start |
| E | Develop requirements matrix | D | Finish-to-Start |
| F | Develop project schedule | E | Finish-to-Start |
| G | Create UI/UX wireframes | F | Finish-to-Start |
| H | Define technical architecture | F | Finish-to-Start |
| I | Build front-end interface | G | Finish-to-Start |
| J | Develop back-end functionality | H | Finish-to-Start |
| K | Integrate tracking system | I,J | Finish-to-Start |
| L | Perfom System Testing | K | Finish-to-Start |

| Activity | Description | Duration |
| --- | --- | --- |
| A |  |  |
| B |  |  |
| C |  |  |
| D |  |  |
| E |  |  |
| F |  |  |